# Project Charter — ERP Phase 2

Project ID: P-01 | CONFIDENTIAL | Version: 1.2

## Project Overview

ERP Phase 2 is the most critical IT initiative for FY2025. Full migration to Pinoy Cloud ERP covering Finance, HR, and Operations. Target completion: December 2025.

| Field | Details |
| --- | --- |
| Project Owner | Kevin Navarro |
| Sponsor | Elena Castillo, COO |
| Budget | PHP 3,500,000 |
| Spent to Date | PHP 420,000 (12%) |
| Vendor | Pinoy Cloud ERP — Ben Castro, Implementation Lead |
| Risk Level | HIGH — no fallback system if migration fails |

## Milestones

| Milestone | Target Date | Status | Owner |
| --- | --- | --- | --- |
| Board Approval | Feb 15, 2025 | PENDING | Castillo |
| Vendor Kickoff | Mar 1, 2025 | Not Started | Navarro |
| Finance Module UAT | Jul 31, 2025 | Not Started | Garcia |
| Go Live | Dec 1, 2025 | Not Started | Navarro |

IMPORTANT: Board approval (Feb 15) passed with no decision recorded. No budget released beyond initial PHP 420,000. Timeline will slip one quarter if not resolved by April 1.

## Dependencies

• Pinoy Cloud ERP contract must be finalized before March 1

• IT-004 server replacement required before data migration

• Finance team must close FY2024 books before Finance module migration

Prepared by: Kevin Navarro | Last reviewed: March 2025