## Master Tracker
PROJECT MASTER TRACKER — All Departments FY2025
ID | Project | Dept | Owner | Priority | Status | Budget | Spent | % Complete | Start | Deadline | Risk | Key Milestone
P-01 | ERP Phase 2 | IT | Navarro | Critical | In Progress | 3500000 | 420000 | 12 | 2025-01-01 | 2025-12-31 | High | Board approval Feb 15
P-02 | Talent Drive Q1 | HR | Magno | High | In Progress | 180000 | 54000 | 30 | 2025-01-15 | 2025-03-31 | Medium | 15 hires by March
P-03 | Product Launch X | Marketing | Aquino | Critical | Delayed | 900000 | 810000 | 85 | 2024-06-01 | 2025-01-31 | High | OVERDUE — missed Jan deadline
P-04 | ESG Report 2024 | Finance | Hernandez | Medium | In Progress | 90000 | 45000 | 50 | 2024-10-01 | 2025-02-28 | Low | SEC submission due
P-05 | Mobile App MVP | IT | Pascual | High | In Progress | 750000 | 187500 | 25 | 2024-11-01 | 2025-05-31 | Medium | Beta by April
P-06 | Regional Expansion | Sales | Rodriguez | Critical | Planning | 5000000 | 0 | 0 | 2025-01-15 | 2025-12-31 | High | No budget released yet
P-07 | Office Renovation | Admin | Castillo | Low | On Hold | 2500000 | 750000 | 30 | 2024-05-15 | 2025-06-30 | High | Permit still pending
P-08 | Customer Portal | IT | Cruz | High | In Progress | 600000 | 300000 | 50 | 2025-01-01 | 2025-06-30 | Medium | UAT starts March
P-09 | FY2025 Audit Prep | Finance | Garcia | Medium | Not Started | 120000 | 0 | 0 | 2025-03-01 | 2025-09-30 | Low | External auditors booked
P-10 | Sales Training PH | Sales | Santos | Low | Completed | 80000 | 77000 | 100 | 2025-01-05 | 2025-01-31 | Low | Done — under budget